## Agenda
Leadership Cobb 2026 Opening Day
2025-07-30
Time | Item |  | Committee Actions & Information
14:00 | Staff Arrives |  | Kai Lawrence
| Delta SKY360 Club set-up: tables in small pods, 4 chairs around each (default set up) |  | Braves contacts: McKenna Bond (214) 585-7158 & Chris Owens (678) 977-1195
| Set up registration material in the Delta SKY360 Club: Nametags, 2 drink tickets each, parking validation |  | Braves main contact: Kimora Street (201) 208-5919
***Namebadges have red or blue stickers with numbers***
| Set up AV/Run tech ¦ Kai has Blitz Photo PPT |  | Laptop, clicker, HDMI cord
14:30 | Committee Arrrives for Set Up and Prep |  | Opening Day Committee, Memories & Hospitality
| Double check and review Registration station |  | Judy Renfoe & Judy Skeel
| Committee Huddle - Review Agenda and Tasks, Committee Nametags |  | Jess & Corey
| Committee picture in dugout |  | Matt & Allison
| Set up class gift bags |  | All Committee
| Collect corresponding pom pom (red or blue) | Reference Dug Out List
Place agendas and table tents on tables
| WS Trophies on Display (3 PM-5:15 PM) ¦ Red Carpet Entry |  | Committee & Class attire: Braves gear
15:15 | COMMITTEE IN PLACE |  | No later than 3:30 PM
15:45 | Bar opens
15:45 | Movement to Delta SKY360 Club |  | Opening Day Committee
Committee members usher class to elevators
Enthusiastic welcome by committee along the way to Delta SKY360 Club- direct to check in table
Committee stationed accordingly-
3B Gate Lobby: Theresa, Keisha, Kelli & Zach
Hallway: Sheree & Debbie (Greeters & Directions)
Entrance to Delta SKY360 Club: Gerlda & Trooper
Registration: Judy Renfoe, Judy Skeel (Nametags & Drink Tickets)
Delta SKY360 Club: Corey Ferguson, Jessica Lee & remaining committee
16:00 | Class Arrives at 3rd Base Gate / Check in at Delta SKY360 Club
Cocktail Hour at the Gold Glove Bar
(Rolling Blitz Presentation on all Screens)
16:15 | Welcome by Opening Day Committee Co-Chairs |  | Jess & Corey
Handheld mic (1)
Thank Sponsors: on the agenda!
16:20 | Groups dismissed by nametag color - Gerlda (3rd base - blue) & Eric (1st base - red) |  | Make a PSA before moving to dugouts about drinks & belongings
16:20 | Movement to Dugouts |  | Class follows Opening Day Committee
| Hospitality in Delta SKY360 Club with belongings | Single file to the dugout
Committee members in dugouts to encourage them to line up in numerical order (ice breaker)
16:30 | Chair & Class Announcements - on Field |  | Names and titles on jumbotron; remind class not to bring drinks on field
| Braves Open Video (30 sec) |  | Atlanta Braves Tech
PA Welcome and Class Introductions (Lineup)
| Ceremonial First Pitch |  | Joyeddie
| National Anthem |  | Tre Hutchins - Confirmed by Eric
| LC Chairs Welcome |  | Joyeddie
| Class Photo at Home Plate | *Monument Garden - rain location | Allison Giddens, Matt Giddens
2 handheld mics
16:50 | Delaware North Catering set up |  | Delaware North Catering: TBD
16:55 | Gerlda & Eric ensure nothing is left behind in dugouts/all people are cleared out
17:00 | Speakers arrive - Kai & Keisha |  | Must be off field by this time
17:00 | Return to Delta SKY360 Club through 3rd Base entrance |  | Must be off field by this time
Break for drinks and food
Encourage further meeting of classmates
17:20 | Official Welcome
| Cobb Chamber | 5 minutes | Sharon Mason, Cobb Chamber CEO (LC'12)
17:25 | Sponsor Remarks
| Yearlong Presenting Sponsor | 5 minutes | Robin Cheramie, Kennesaw State University MBA & EMBA Programs – Presenting Sponsor
| Changemaker Sponsor | 2 minutes | Danya Trent, Lockheed Martin
17:32 | Introduction of Speaker |  | Kelli Wolk
17:35 | Keynote |  | Grant Rivera - Confirmed by Kelli
Speech – 20 min
18:00 | Break
18:15 | Heavy Hitters Performance |  | No introduction
18:25 | Drumline Icebreaker Breakouts |  | Geoffrey Schmidt - (407) 408-3080
One Heavy Hitter at each group as 'captain'
Committee Members with each group for support
70s - Debbie Ponder
80s - Sheree Knowles
90s - Kelli Wolk
00s - Eric Baker
10s - Keisha Register
18:30 | Fall Retreat Committee and Chairs Arrive |  | Joy Doss & Tripp Boyer
18:50 | Drumline Icebreaker Performances
19:10 | Fall Retreat Introduction & Preview |  | Joy Doss & Tripp Boyer
Explain the purpose and FUN of skit groups
Provide instruction for huddle breakout session: exchange contact info/make groupme
Provide context for the baseball cards "know your cards"
19:15 | Skit Group Huddles |  | Joy Doss & Tripp Boyer
70s - Debbie Ponder + Tori O'Bryant
80s - Sheree Knowles + Kristen Lord
90s - Kelli Wolk + Chris Martin
00s - Eric Baker + Daniel Cummings
10s - Keisha Register + Mike Cunningham
19:25 | Set up goodie bags at check in station
19:40 | Thank you and Closing Remarks
| Thank You: Committee, Memories, Braves, Sponsors |  | Jess & Corey
| Reminder of upcoming events |  | Joyeddie
** Remind everyone to take a goodie bags when leaving
** Remind everyone to know their cards
19:45 | Last Call at the Bar
20:00 | Adjorn and Clean Up
Pack up as needed
20:15 | Clear Out of Space

## Packing List
Packing List:
Class Agendas
Committee Agendas
Nametags - class | Red and blue stickers
Sponsor signs for registration | Easel for sponsor sign
Dugout rosters
Contact lists – class, committee, and major POCs with Braves/Delaware North, etc.
Scripts (PA & program)
Table tents w/sponsors
Dug out lists
Laptop with HDMI cord
Pom poms
Red and blue stickers
Goodie Bags:
Fall Retreat Cards
Sponsor Items
Fall Retreat Brochures
Thank You Cards
Class attire
FR Preview:
Skit instructions
Decade contact sheets
sample brochure